## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Luis | Daniel | Anh | Parnian | Total
|  | Task Description | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2 | 2 | 2 |  |  | 4
|  | Design architecture | Project Manager, Requirements Engineer | Luis, Daniel | 2 |  | 2 |  | 2 | 2 |  |  | 4
| Requirements |  |  |  |  | 9 |  | 9 | 9 | 9 | 0 | 0 | 18
|  | Gather | Project Manager, Requirements Engineer | Luis, Daniel | 2 |  | 3 |  | 3 | 3 |  |  | 6
|  | Analyze | Project Manager, Requirements Engineer | Luis, Daniel | 4 |  | 3 |  | 3 | 3 |  |  | 6
|  | Specify | Project Manager, Requirements Engineer | Luis, Daniel | 3 |  | 3 |  | 3 | 3 |  |  | 6
| Documentation |  |  |  |  | 28 |  | 38.5 | 24.5 | 24.5 | 15.5 | 18.5 | 83
|  | Project Charter | Group | Luis, Daniel | 2
|  | Release Plan | Group | Daniel, Luis, Parnian, Anh | 2 |  | 3.5 |  | 3.5 | 3.5 | 3.5 | 3.5 | 14
|  | Requirements Document | Project Manager, Requirements Engineer | Luis, Daniel | 5 |  | 6.5 |  | 6.5 | 6.5 |  |  | 13
|  | Project Plan | Group | Daniel, Luis, Parnian, Anh | 5 |  | 8 |  | 8 | 8 | 8 | 8 | 32
|  | Architecture Document | Architect | Anh | 4 |  | 4 |  |  |  | 4 |  | 4
|  | Test Report | Group | Daniel, Luis, Parnian, Anh | 8 |  | 7 |  |  |  |  | 7 | 7
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Daniel, Parnian | 2 |  | 6.5 |  | 6.5 | 6.5 |  | 0 | 13
Coding | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 51 |  | 37 | 21 | 18 | 15 | 22 | 76
|  | Determine technology needs | Group | Daniel, Luis, Parnian, Anh | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Research and learn new language and environment | Group | Daniel, Luis, Parnian, Anh | 10 |  | 10 |  | 10 | 10 | 10 | 10 | 40
|  | Set up proxy server software | Developer | Parnian | 8 |  | 3 |  | 0 | 0 | 0 | 3 | 3
|  | Write basic proxy code | Requirements Engineer | Daniel | 5 |  | 5 |  | 0 | 5 | 0 | 0 | 5
|  | Implement classes | Project Manager | Luis | 10 |  | 8 |  | 8 | 0 | 0 | 0 | 8
|  | Create HTTP handling code | Developer | Parnian | 8 |  | 3 |  | 0 | 0 | 0 | 3 | 3
|  | Write code to store user name locally | Architect | Anh | 2 |  | 2 |  | 0 | 0 | 2 | 0 | 2
|  | Write code for managing HTTP session | Developer | Parnian | 5 |  | 3 |  | 0 | 0 | 0 | 3 | 3
|  | Unit Testing | Group | Daniel, Luis, Parnian, Anh | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 8
| Analysis |  |  |  |  | 6 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | System Testing | Group | Daniel, Luis, Parnian, Anh | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bug fix as required | Group | Daniel, Luis, Parnian, Anh | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Group | Daniel, Luis, Parnian, Anh | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Iteration 2: | Design |  |  |  |  | 12 |  | 0 |  |  |  |  | 0
|  | Implement any design changes | Requirements Engineer, Developer | Daniel, Parnian | 4
|  | Set up HTML content for home page | Requirements Engineer, Developer | Daniel, Parnian | 4
|  | Style homepage content with CSS | Requirements Engineer, Developer | Daniel, Parnian | 6
|  | Set up Bootstrap for home page | Requirements Engineer, Developer | Daniel, Parnian | 2 | [7 empty] | 0
|  | Create UI design for home page | Requirements Engineer, Developer | Daniel, Parnian | 2
| Development |  |  |  |  | 22 |  | 30 |  |  |  |  | 0
|  | Implement classes | Project Manager, Architect | Luis, Anh | 8
|  | Implement Databases | Project Manager, Architect | Luis, Anh | 5
|  | Link databases together with relationships and foreign keys | Project Manager, Architect | Luis, Anh | 10
|  | Implement UI | Project Manager, Architect | Luis, Anh | 4
|  | Unit Testing | Project Manager, Architect | Luis, Anh | 2
| Analysis |  |  |  |  | 6 |  | 5.5 |  |  |  |  | 0
|  | System Testing | Group | Daniel, Luis, Parnian, Anh | 2
|  | Bug fix as required | Group | Daniel, Luis, Parnian, Anh | 2
|  | Evaluate needs for next iteration | Group | Daniel, Luis, Parnian, Anh | 2
Iteration 3: | Design |  |  |  |  | 22 |  | 7.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager |  | 2 |  | 0.5 |  | 0.5 |  |  |  | 0.5
|  | Risk analysis | Project Manager |  | 2 |  | 1 |  | 0.5 | 0.5 |  |  | 1
|  | Create UI design for vendor locations | Developer |  | 10 |  | 4 |  | 1 |  |  | 3 | 4
|  | Design data structure for RSS location list | Developer |  | 8 |  | 2 |  | 2 |  |  |  | 2
| Development |  |  |  |  | 29 |  | 5 |  |  |  |  | 0
|  | Review requirements | Developer |  | 1 |  | 0 | [5 empty] | 0
|  | Develop code for processing vendor locations | Developer |  | 10 |  | 3 |  |  |  |  | 3 | 3
|  | Implement vendor map display | Developer |  | 8 |  | 0 |  |  |  |  | N/A | 0
|  | Display vendor information | Developer |  | 8 |  | 2 |  |  |  |  | 2 | 2
|  | Unit Testing | Developer |  | 2 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 5 |  | 2.1 |  |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager |  | 3 |  | 1.5 |  | 1 | 0.5 |  |  | 1.5
|  | Bug fix as required | Tester, Developer |  | 2 |  | 0.6 |  | 0.5 |  |  | 0.1 | 0.6
Total |  |  |  |  | 202 | 202 | 108.2 | 108.2 | 24.5 | 39.5 | 22 | 22.2 | 108.2